## BRANDING PROJECT
Project planning SG organised event
Time in month up to your conference
| 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | event | after
Pre-Conference
Communication with IWA
Proposal sent to the IWA | x
Approval progress of the IWA |  | x | x | x | x | x | x
Sent a short paragraph to the IWA for our magazine water 21 + website | [6 empty] | x
Prepare delegate list | [23 empty] | x
Keep the IWA informed about all changes | [6 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
Submission
Call for papers | [6 empty] | x
Publish deadline for submission | [6 empty] | x | x | x | x | x | x | x | x | x | x | x | x
Deadline for submission-review process starts | [17 empty] | x
Acknowledge receipt of all abstracts | [6 empty] | x | x | x | x | x | x | x | x | x | x | x | x
Tell authors/presenter about their acceptance/rejection | [18 empty] | x
Partners
Send out sponsorship brochure and write to potential sponsors | [11 empty] | x
Identify and contact chairs | [20 empty] | x
Provide marketing material to sponsors & exhibitors | [20 empty] | x
Organise local helpers -on site support | [22 empty] | x
Programme
Inform authors/presenters well about their slots in the programme | [18 empty] | x
Decide on and publish programme | [18 empty] | x
Consider conference dinner arrangements | [19 empty] | x
Confirm conference dinner booking | [20 empty] | x
Print programme book | [23 empty] | x
Registration
Call for registration | [18 empty] | x
Print registration brochure and send out | [19 empty] | x
Deadline for early registration | [21 empty] | x
Produce tickets (Gala dinner/reception/lunch) | [21 empty] | x
Other Advertisement
Set up website | [6 empty] | x
Set up conference database | [20 empty] | x
Generic advert | [20 empty] | x | x | x | x
Local marketing | [20 empty] | x | x | x | x
Send out marketing email/flyer and registration brochure to previous delegates | [20 empty] | x
Venue
Consider catering arrangements - type/place | [20 empty] | x
Finalise catering /other arrangements with venue - detailed venue confirmation letter | [23 empty] | x
Detailed briefing of the venue (Chairs, podiums....) | [23 empty] | x
Staff
Arrange accommodation and travel for staff | [21 empty] | x
Prepare Staffing schedule/ have trainee meeting for everybody involved | [23 empty] | x
For delegates\presenters
Order conference bags | [22 empty] | x
Organise poster boards | [22 empty] | x
Prepare badges | [23 empty] | x
Prepare delegate packs | [23 empty] | x
Prepare evaluation form | [23 empty] | x
During the conference
Liaison with speakers/ poster presenters | [24 empty] | x
On site delegate registration desk | [24 empty] | x
On site marketing for IWA-memberships | [24 empty] | x
Provide briefing for on site staff | [24 empty] | x
Keep the IWA informed about all changes | [24 empty] | x
After the conference
Send delegate list to the IWA | [25 empty] | x
Send out speaker thank you letters & process payment | [25 empty] | x
Debrief venue, conference and marketing | [25 empty] | x
Feedback meeting with committee | [25 empty] | x
Reconciliation of budget | [25 empty] | x
Keep the IWA informed about all changes | [25 empty] | x